# SyncForge 1.1.0 — GitHub Issues Breakdown

Milestone: Wire-up · Injectable HTTP · EntityStore · Auth hardening

Document date: 7 July 2026
Baseline: 1.0.0 GA
Source: docs/ROADMAP_1_0_TO_2_0.md § 1.1.0 GitHub issues breakdown

# Release goal

Ship 1.1.0 with P0 network and entity-store tracks complete, security/cursor/docs P0 done, and no breaking changes to 1.0 stable APIs. P1 integration artifacts (syncforge-integration-*, syncforge-store-realm) may ship in 1.1.1 if needed.

## Labels

Milestone: 1.1.0

Epic labels: epic:network, epic:store, epic:security, epic:dx, epic:release

Area: area:network, area:store, area:security, area:dx, area:docs

Priority: priority:p0, priority:p1, priority:p2

## Suggested timeline (6 weeks, part-time)

| Week | Focus |
| --- | --- |
| 1–2 | A1→A2 (SyncHttpClient, RestSyncTransport) ∥ B1→B2 (EntityStore, @SyncForgeStore) |
| 3–4 | A4 httpClient DSL · B3/B4 store adapters · E1 DataStore cursor |
| 5 | C1/C2 token security · D1 DI recipes · docs (A5, B5) |
| 6 | D2/D3 optional · F1 BOM · acceptance F2 → tag F3 |

# Epic A — Injectable HTTP client (P0)

| Issue | Title | Job ID | Depends on | Done when |
| --- | --- | --- | --- | --- |
| A1 | feat(network): add SyncHttpClient contract in commonMain | 1.1-13 | — | postPush/getPull API; fake-client unit tests |
| A2 | feat(network): RestSyncTransport delegates to SyncHttpClient | 1.1-14 | A1 | KtorSyncTransport delegates internally; external API unchanged |
| A3 | refactor(network): extract :syncforge-network-ktor adapter | 1.1-15 | A2 | Ktor wiring in optional module |
| A4 | feat(dsl): httpClient { } on platform DSLs | 1.1-16 | A2 | Injected app HttpClient; bundled fallback |
| A5 | docs(network): injectable HttpClient guide | 1.1-12 | A4 | GETTING_STARTED + RECIPES interceptors sample |

# Epic B — EntityStore abstraction (P0)

| Issue | Title | Job ID | Depends on | Done when |
| --- | --- | --- | --- | --- |
| B1 | feat(store): EntityStore contract in commonMain | 1.1-09 | — | CRUD + transaction; maps to EntitySyncHandler |
| B2 | feat(ksp): @SyncForgeStore handler generation | 1.1-10 | B1 | @SyncForgeDao path unchanged |
| B3 | feat(store): :syncforge-store-room adapter | 1.1-11 | B2 | Optional Maven artifact; not in core BOM transitives |
| B4 | feat(store): in-memory EntityStore for commonTest | 1.1-11 | B1 | Non-Room path without Realm |
| B5 | docs(store): BYO store path in GETTING_STARTED | 1.1-12 | B2, B4 | Room optional; plugin skips Room KSP when unused |

# Epic C — Auth & token security (P1, GA-required)

| Issue | Title | Job ID | Depends on | Done when |
| --- | --- | --- | --- | --- |
| C1 | feat(auth): encrypted TokenStore (Android + iOS Keychain) | 1.1-17 | — | Migration from plain prefs documented |
| C2 | feat(auth): login/register CharArray overloads | 1.1-18 | — | Wipe in finally; AUTH_API updated |
| C3 | api(auth): graduate built-in auth DSL to stable | 1.1-04 | C1, C2 | Remove @ExperimentalSyncForgeApi on auth surfaces |

# Epic D — DI & developer experience

| Issue | Title | Job ID | Depends on | Done when |
| --- | --- | --- | --- | --- |
| D1 | docs(dx): Koin + Hilt recipes in RECIPES.md | 1.1-01 | B1 | No Koin/Dagger in :syncforge core |
| D2 | feat(dx): publish syncforge-integration-koin | 1.1-02 | D1 | syncForgeModule { } + WorkManager helper |
| D3 | feat(dx): publish syncforge-integration-hilt | 1.1-03 | D1 | @Provides templates |
| D4 | feat(sample): optional :sample-di variant | 1.1-06 | D2 or D3 | Documented DI wiring |

# Epic E — Cursor persistence (P1)

| Issue | Title | Job ID | Depends on | Done when |
| --- | --- | --- | --- | --- |
| E1 | feat(persistence): DataStore Preferences pull cursor (Android) | 1.1-05 | — | iOS UserDefaults fallback documented |

# Epic F — 1.1.0 release gate

| Issue | Title | Job ID | Depends on | Done when |
| --- | --- | --- | --- | --- |
| F1 | chore(dist): BOM lists optional 1.1 artifacts | acceptance | A3, B3 | Store/network/integration in BOM constraints only |
| F2 | test(qa): 1.1.0 acceptance matrix | § criteria | A*, B*, C*, D1, E1 | All acceptance checkboxes green |
| F3 | chore(release): tag v1.1.0 + Maven Central publish | 1.1-08 | F2 | CHANGELOG; verify workflow |
| F4 | docs: MODULES + CHANGELOG 1.1.0 freeze | — | F2 | Stability table updated |

# 1.1.0 acceptance criteria

SyncHttpClient + RestSyncTransport published; KtorSyncTransport backward compatible

Injectable Ktor HttpClient documented with app-owned client sample

EntityStore in commonMain; EntitySyncHandler delegates through it

KSP generates handlers from @SyncForgeStore and existing @SyncForgeDao

Non-Room path documented (in-memory store test or recipe)

RECIPES.md DI section — Koin + Hilt examples

DataStore cursor on Android; iOS fallback documented

Encrypted TokenStore default; CharArray login/register overloads

BOM lists optional integration + store artifacts (not transitive)

No breaking changes to 1.0 stable APIs

# 1.0.x patch lane

Job 1.1-08: semver patches on 1.0.x branch only — bugfixes, no new APIs. main targets 1.1.0 feature work.

# Related documents

| Document | Purpose |
| --- | --- |
| docs/ROADMAP_1_0_TO_2_0.md | Markdown source — full 1.1.x architecture |
| docs/ROADMAP.md | High-level next: 1.1.0 summary |
| docs/SyncForge-Roadmap-1.0-to-2.0.docx | Full roadmap Word export |